## WSJF Values
User Story | User-Business Value | Time Crtiticality | Risk Reduction | Cost of Delay | Job Size | WSJF
In order to have a fresh view of my service me as service owner I want to receive a daily recap each morning. | 5 | 13 | 5 | 23 | 5 | 4.6
in order to drive a transparency culture as TOP manager I want to have all the Critical Performance Indicators published on screens. | 3 | 3 | 3 | 9 | 3 | 3
In order to take real time decisions, me as service owner I want to have Technis integrated online with the ticketing system. | 8 | 13 | 8 | 29 | 8 | 3.625
In order to increase performances and drive savings of 10% me as service owner I want to have suggested and automated Root Cause Analysis | 13 | 20 | 13 | 46 | 20 | 2.3
In order to increase performances and drive savings of 10% me as service owner I want to have a proactive view on service degradation risks | 20 | 20 | 20 | 60 | 20 | 3

## Settings
1
2
3
5
8
13
20
40